## Schedule 2026-11
Villa | Block | Activity | Planned Start | Planned End | Notes
V12 | B | Column Reinforcement | 2026-11-01 18:30 | 2026-11-04 18:30 | Carried over from October, remaining 30%
V12 | B | Column Concreting | 2026-11-05 18:30 | 2026-11-06 18:30
V12 | B | Shuttering First Slab | 2026-11-08 18:30 | 2026-11-13 18:30
V12 | B | First Slab Concreting | 2026-11-15 18:30 | 2026-11-16 18:30 | Contingent on rebar delivery by 14-Nov
V15 | B | Internal Plastering | 2026-11-02 18:30 | 2026-11-17 18:30
V15 | B | External Plastering | 2026-11-09 18:30 | 2026-11-24 18:30
V15 | B | Electrical First Fix | 2026-11-14 18:30 | 2026-11-27 18:30 | Needs electrical drawings issued by 12-Nov
V18 | C | Earthwork | 2026-11-01 18:30 | 2026-11-05 18:30
V18 | C | PCC | 2026-11-06 18:30 | 2026-11-07 18:30
V18 | C | Footing Reinforcement | 2026-11-08 18:30 | 2026-11-12 18:30
V18 | C | Footing Concreting | 2026-11-13 18:30 | 2026-11-14 18:30
V18 | C | Plinth Beam Reinforcement | 2026-11-16 18:30 | 2026-11-20 18:30
V21 | C | Masonry Ground Floor | 2026-11-01 18:30 | 2026-11-19 18:30
V21 | C | Lintel Shuttering | 2026-11-20 18:30 | 2026-11-23 18:30
V21 | C | Lintel Concreting | 2026-11-24 18:30 | 2026-11-25 18:30
V24 | D | Flooring Underbed | 2026-11-01 18:30 | 2026-11-08 18:30
V24 | D | Flooring Tile Laying | 2026-11-09 18:30 | 2026-11-23 18:30
V24 | D | Plumbing First Fix | 2026-11-04 18:30 | 2026-11-17 18:30
V27 | D | Internal Putty | 2026-11-01 18:30 | 2026-11-11 18:30
V27 | D | Internal Primer | 2026-11-12 18:30 | 2026-11-17 18:30
V27 | D | Internal Paint First Coat | 2026-11-18 18:30 | 2026-11-25 18:30 | Window frames to be masked beforehand

## Rules
Rule | Detail
File name | contractor-schedule-<YYYY-MM>.xlsx. One file per month, replaces last month's.
Scope of each file | Only activities planned for THIS month. Future months come in future files.
Granularity | One row per activity per villa. The same activity on V12 and V15 is two rows.
Activity names | Match the names the Siddhi WBS uses. Minor spelling or trailing-text differences are OK; Siddhi previews a fuzzy match for Vandana to confirm each unclear row before saving.
Dates | Excel date cells. DD-MMM-YYYY in display is ideal (03-Nov-2026). Both Planned Start and Planned End are required.
Carryovers | Activities started in a previous month still include the remaining-work window. Add a short note so Siddhi can tag it.
Corrections | Re-upload with the same file name. Siddhi shows a diff and replaces the previous version.
What NOT to include | Hidden sheets, merged cells, formulas that reference other sheets, blank rows between activities. Keep the Schedule sheet flat.
Notes column | Free text, up to 500 characters. Use for contingencies (material delivery, drawing issuance, interface with other trades).
Signal Siddhi applies | Siddhi compares each row's Planned End to the in-house planned end for the same activity. Green = comfortable buffer, Orange = within 5-10 days, Red = at or past the in-house end.